## Sheet1
| Instructions: Modify this sheet to estimate your integration costs by modifying the rates and hours in the cells highlighted in light green. |  | Biz FTE - hrly rate: |  |  | 40 | Dev FTE - hrly rate: |  |  | 60 | Exec FTE - hrly rate: |  |  | 100 | TOTAL TIME (hours) |  |  | TOTAL COST
|  |  | Low End |  | Top of Range |  | Low End |  | Top of Range |  | Low End |  | Top of Range
Task | Objective | Sub-Tasks | Hrs | Cost | Hrs | Cost | Hrs | Cost | Hrs | Cost | Hrs | Cost | Hrs | Cost | LOW | HIGH | MEDIAN | LOW | HIGH | MEDIAN
Determine Fit | Answers: Does the DMS have APIs which meet what I need, how do they work, will they let me integrate? | Online research, one-on-one consultations with DMS, specification review (by IT resource). Internal analysis, presentation and stakeholder alignment. | 16 | 640 | 60 | 2400 | 2 | 120 | 16 | 960 | 2 | 200 | 8 | 800 | 20 | 84 | 52 | 960 | 4160 | 2560
Contract | Set and bind terms of agreement. | Review contract, negotiate red lines, finalize with lawyer review. | 2 | 80 | 12 | 480 |  | 0 |  | 0 | 1 | 100 | 4 | 400 | 3 | 16 | 9.5 | 180 | 880 | 530
Develop | Develop your system to meet the publisher's API integration specification | Write calls, develop fields, transform IDs, test |  | 0 |  | 0 | 120 | 7200 | 480 | 28800 |  | 0 |  | 0 | 120 | 480 | 300 | 7200 | 28800 | 18000
Test & Certify | Gain publisher's agreement that system meets all requirements. | Fulfill all test cases set by publisher, make any necessary code adjustments, and retest if necessary. | 2 | 80 | 8 | 320 | 16 | 960 | 80 | 4800 |  | 0 |  | 0 | 18 | 88 | 53 | 1040 | 5120 | 3080
Pilot | Verify that code works in production with limited rollout at 1-2 pilot locations | Coordinate with publisher on pilot location, activate pilot including install, coordinate tests, monitor results, adjust code if necessary | 24 | 960 | 50 | 2000 | 0 | 0 | 12 | 720 |  | 0 |  | 0 | 24 | 62 | 43 | 960 | 2720 | 1840
Production Maintenance (costs annualized) | Provide production support, maintain function with publisher updates, and audit for contract terms | Support live integrations, re-code for any publisher system releases, and monitor transactions for billing/contract purposes (1-6 hours monthly x 12) | 6 | 240 | 48 | 1920 | 40 | 2400 | 160 | 9600 |  | 0 |  | 0 | 46 | 208 | 127 | 2640 | 11520 | 7080
[14 empty] | Hours | 231 | 938 | 584.5 | 12980 | 53200 | 33090
[14 empty] | Days | 28.875 | 117.25 | 73.0625
[14 empty] | Weeks | 5.775 | 23.45 | 14.6125